## Gantt Chart
Project Plan for the next 12 weeks
Task | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12
Freely suspended mirrors + laser test
Soldering connectors & wiring (besides OSEM)
OSEM PCB testing
Coil winding + solder PD/LEDs + OSEM callibration
Set up DAQ using a breakout board + red pitayas
Simple circuit testing (data logger, coil actuation tests)
Implementing a basic local damping control loop
Setting up the actual control loop
Setting up a suspended fabry-perot cavity